## Sheet1
Site Name CRP Implementation |  |  | Quarter
Schedule of Milestones | Lead | Deliverables
Phase 1: Preparation
Obtain necessary policies/approvals |  | Necessary Board approvals, CRP Policies in place
Discuss move to CRP with Chiefs, Board, Risk Management staff, etc.
Phase 2: Building a Frame (Internal)
Map facility case review process |  | Clear process with CRP overlayed
Review all Best Practices in Playbook with Risk/Safety teams |  | Deep knowledge of CRP program by staff closest to adverse event resolution
Train communication coaches and develop on-call system |  | Disclosure coaching available 24/7
Revise patient facing materials adding CRP language |  | All outgoing patient materials reference CRP and/or match with transparent philosophy
Set up method for internal communications and resources for staff/physicians around CRP process |  | CRP Intranet page or similar method of information push/extraction
Modify incident reporting systems |  | Incident reporting system and patient feedback system can track or assist in tracking disclosure and can flag potential CRP cases
Educate clinicians about CRP |  | All clinicians know who to reach out to and what to do if they are part of an adverse event
Progress check-ins |  | Work through implementation challenges with MACRMI
Phase 3: Building a Frame (External/Insurer)
Review CRP Insurer Best Practices with Insurer |  | Deep knowledge of CRP program at insurer
Develop Plan with Insurer for process of referring CRP Insurer cases and handling 60L letters, and updating all |  | Clear process for handling all CRP cases
Phase 4: Launch
Case Tracking |  | Tracking tool used in CRP program on incoming cases
Official Program Launch |  | Officially begin collecting data
Data Collection |  | Data for dashboard/collaborative
Phase 5: Sustain
Educate clinicians about CRP |  | All clinicians know who to reach out to and what to do if they are part of an adverse event
Review comparative data |  | Make changes or inquiries based on comparative data
|  |  |  | Key | Current Planned Completion
Completed on Time
Delay
Original Planned Completion (due to Delay)