## Clinician & Peer Support
Peer Support Work Plan
Hospital Name
Timeline
Advisory Members
Project Manager/Admin Name & Contact
Milestone | Tasks | Start Date | End Date | Owner | Status | Notes
Getting Started | Month 1
| Establish a peer support advisory committee |  |  |  |  | BLC has guidance doc on this | Delayed
Identify project manager
Schedule reoccurring monthly meetings with the advisory committee
Select department and unit to implement pilot program
Select Peer Supporters | Month 2
Send out organization-wide communication on the pilot program
Secure training date and space
Develop plan to identify peer supporters and execute
Monthly meeting with the team
Send out selection letters to identified peer supporters
Create a detailed calendar for one year of events for trainings, support for supporters, advisory commmittee meetings
Peer Support Training Planning | Month 3
Monthly meeting with team
Develop a marketing plan
Create logo, brochures, handouts about internal resources along with external resources
Conduct internal and external scan of support resources available
Decide where program will be anchored and internal process
Create training agenda
Identify internal support to present at training
Discuss option of CEUs for the training
Conduct Pre-Survey (optional) | Month 5
In-person meeting with advisory team
Conduct pre-survey
Peer Support Training | Month 6
Conduct peer support training
Administer training evaluation
Provide the schedule for the upcoming support for the supporter meetings
Monthly meeting with team
Send out communications to peer supporters about "Support for peer supporters" meeting (held in months 7, 9, and 11)
Post-Training Consultation | Month 7
Monthly meeting with team
Hold first support for supporters meeting
Send out communications about support for peer supporters meeting (held in month 9)
Begin tracking peer support interactions
Create a short slide deck for internal informational/marketing info re: site.
Set date for next peer support training in month 12 and secure space
Month 8
Monthly meeting with advisory committee
Send save the date for the next peer support training
Track peer support interactions
Month 9
Support for the peer supporters meeting
Monthly meeting with advisory committee
Track peer support interactions
Month 10
Monthly meeting with advisory committee
Hold meeting with the Betsy Lehman Center and team doing the peer support training
Track peer support interactions and submit to Betsy Lehman Center
Month 11
Monthly meeting with advisory committee
Support for the peer supporters meeting
Track peer support interactions
Month 12
Hold second peer supporter training and evaluation
Monthly meeting with advisory committee
Track peer support interactions
Month 13
Monthly meeting with advisory committee
Support for peer supporters meeting
Track peer support interactions and submit to project manager
Month 14
Monthly meeting with advisory committee
Track peer support interactions
Month 15
Monthly meeting with advisory committee
Support for peer supporters meeting
Track peer support interactions
Month 16
Monthly meeting with advisory committee
Track peer support interactions and submit to project manager
Month 17
Monthly meeting with advisory committee
Track peer support interactions
Evaluation | Month 18
Monthly meeting with advisory committee
Distribute post survey
Track peer support interactions
Submit peer support tracking to project manager
Separate debriefing meeting with the advisory committee (and others if needed) to talk about the entire process as a whole
Month 21
Final meeting with advisory committee and Betsy Lehman Center team to discuss survey data